## MARCH 7
MINUTES OF THE MARKETING MEETING | ACTION PERSON | TIME
HELD ON MARCH 7TH, 2025.
PRESENT
1. Jane Gichuki– Managing Director
2. Hazel Wananyanga - Operations Manager
3. Desmond kithinji -Marketing Executive
4. Kelvin Murerwa- IT Manager
5. Valentine Wanjiku - Marketing Executive
6. Diana Arunga – Marketing Executive
AGENDA
1. Matters arising from the reading of the previous minutes and seconded by Valentine.
2. Events
3. Updates on previous marketing tasks
4. Marketers reports.
5. AOB.
The meeting commenced with a word of prayer from Desmond.
MINUTE 1: MATTERS ARISING.
Ø Reading of the previous minutes done by Daina.
MINUTE 2: EVENTS
Ø Team was tasked to make analysis on which category of groups have not been giving bussiness. | all marketers
ØMarketers were advised make a proposal for group swimming rates | all marketers
Ø To come with a plan and reasearch on Nairobi accounts for easy facilition . | all marketers
MINUTE 3: UPDATES ON PREVIOUS MARKETING TASKS
Ø A presentation of the analysis of room occupancy per category from October 2024 , November 2024, December 2024 and January 2025. | DESMOND
Ø A presentation of the Market survey analysis of beer prices in the region | Diana
Ø A presentation of the accommodation and conferencing rates in the region. | Valentine
Ø A presentation of the emerging trends in the hospitality industry. | ALL marketers
MINUTE 4: MARKETERS REPORT | all marketers
NOTES BY THE MD :
Ø She adviced we do analysis of beer bucket sold with food and without for comparison. | all marketers
Ø She recommended marketers to acqired a driving license for own benefit and minimise cost as company have vehicle to be used. | all marketers
Øwe try to transit from old rates before end of march.i.e conferining and other approved rates.
Ø Reommended Tumbukiza half kg to bbe added to system. | Kelvin
Ø we try analysing were bussiness have been not coming i.e from groups like schools and churches.
Ø o come with a proposal for rates swimming on groups | all marketers
Ø She approved new beers price and to start selling by 10th March 2025 .
NOTES BY THE OPERATIONS MANAGER:
Ø Proposed that we scrap deluxe rooms as they don’t sell often
Ø Proposed Gala dinners we should try and sell some items like alchol and accomodation on discounts to generate revenue
ØShe proposed we try selling co oparates tables during events we host
Ø Mentioned on performace done in mayan sarova was good we should emulate it.
ØStated that promotins or parternship with other brands during or events and holidays
Ø She tasked Valentine to re work on easter program and share
Ø She mentioned swimming packages for groups rates should be reworked .
NOTES BY DESMOND:
Ø Give summury of previous week account visited and plans for next week visit
Ø Briefly give feedback on visit to FK club launch.
Ø He mentioned we had good reviews on groups from last week..
NOTES BY VALENTINE
Øbreifly Give feeback and report on FK club launch,and interaction with media hosts.
Øshe give report on conferening rates in region.
Øshe give report on EXPO she attended and shared materials for reference.
Øshe said we got positive feedback from I.C.E.A group
Ø Presented easter program and cowboy theme
NOTES BY DIANA
Ø Give a brief report on Sarova Mayans on visit,mentioned it was good expirence,aslo mentioned about their promotion and parternship with other brands
Ø Give a report for accounts visited last week and plans for next week. | kelvin
Ø Design creative QR code to push guest rating us on Tripadvisor. | kelvin
Ø Try to incoporate young people activites as they are left out and are majority
Ø Presented proposed uniforms and prices
NOTES BY KELVIN
.
MINUTE 5: AOB:
There being no other business the meeting was closed by a word of prayer by Valentine.
NAME:
SIGN:
DATE:
NAME:
SIGN:
DATE:

## MARCH 14
MINUTES OF THE MARKETING MEETING | ACTION PERSON | TIME
HELD ON MARCH 14TH, 2025.
PRESENT
1. Jane Gichuki– Managing Director
2. Hazel Wananyanga - Operations Manager
3. Desmond kithinji - Marketing Executive
4. Kelvin Murerwa- IT Manager (Recording member)
5. Valentine Wanjiku - Marketing Executive
6. Diana Arunga – Marketing Executive
7. William Juma - Food & Beverage Manager
AGENDA
1. Matters arising from the reading of the previous minutes.
2. Events.
3. Updates on previous marketing tasks.
4. Marketers reports.
5. AOB.
The meeting commenced with a word of prayer from Desmond.
MINUTE 1: MATTERS ARISING.
Reading of the previous minutes done by Desmond.
MINUTE 2: EVENTS
Valentine presented a proposal to host a run in June.
The health club team together with Kelvin were tasked with route mapping for the run. | Health club & Kelvin
It was suggested that there be the following categories in the run; 21km, 15km, 10km and 5km to accommodate everyone.
The run will be open to employees, guests and the local community.
Valentine was tasked to engage Nyeri county running club organisers for a potential partnership.
Refreshments and entertainment were also suggested to help boost numbers.
She aslo gave updates on Easter entertainment program.
MINUTE 3: UPDATES ON PREVIOUS MARKETING TASKS
Marketers to come up with a proper plan on how ther are going to penetrate Nairobi market. | Marketers
Desmond submited a budget proposal for Nairobi market entrance facilitation. MD said she would go through it and give feeedback.
MINUTE 4: MARKETERS REPORT
NOTES BY THE MD :
She directed that beers sales be part of duty manager's report everyday.
She tasked Diana to follow up and convert Effort Junior Schools in Kerugoya. | Diana
She insisted on thorough group profiling for enhanced customer satisfaction.
She advised marketers to properly map their coverage for better results.
She tasked Valentine to monitor beer and food sales to assess whether the discount on beers is worth it. | Valentine
She tasked Desmond to visit Ontulili Boys High School for potential business. | Desmond
She advised the team to start small with the run and learn from it because a full marathon has many many logistical issues.
She directed that marketers fill accounts visited every end of day Thursday without fail to prevent any conflicts about acccount ownership. | All marketers
NOTES BY THE OPERATIONS MANAGER:
She gave a report on the performance of a lar carte sales since the introduction of discounts on beers.
She asked the team to polish the Easter program and budget for approval.
She asked Diana to share a quotation for the sip and paint proposal with her.
She asked marketers to provide in advance a group's special requirements for for proper planning.
NOTES BY DESMOND:
He reported that he had visited several accounts in Mukuweini and Nyeri including Wakulima Sacco.
He reported that Mukuruweini law courts are under a tight budget. MD advised that the team should deprioritize judiciary accounts.
He mentioned that he would visit meru and Karatina for the proceeding week.
NOTES BY VALENTINE
She reported that she had been to Nairobi for the week.
She said she had planned to introduce Diana and Desmond to Nairobi market but MD advised that they first plan out everything and submit a wholesome proposal to her for review and approval.
She mentioned that she would visit Kirinyaga for the next week.
She requested Hazel to engage Maryanne for a sponsorship on water for the Saturday morning runs. | Hazel
NOTES BY DIANA
She reported that she had been in the hotel for the entire week.
She reported that she would visit Kerugoya and Embu for the next week.
NOTES BY WILLIAM
He asked Kelvin to update QR menu code prices.
He said he woul come up with a new promo to replace Choma brews since it had been rendered ineffective by the discounts on beers. | Juma
NOTES BY KELVIN
He suggested that Heron hall should always be ready for selling as a conference hall. Juma to ensure the hall is always neat. | Juma
Heron hall has no permanent internet provision. Kelvin to follow up. | Kelvin
He reported that two HDMI cables are faulty hence affecting customer experience. | Juma & Kelvin
He reported that that DSTV has pure streaming packages at KES 3,900 and 6,800 respectively. MD advised that we explore alternative ways to stream football matches.
He also reported that the pool table/darts area has poor lighting. | Kelvin
He aslo reported that pool table had sold 9 tickets.
MINUTE 5: AOB:
There being no other business the meeting was closed by a word of prayer by William.
NAME:
SIGN:
DATE:
NAME:
SIGN:
DATE:

## MARCH 28
MARKETING MEETING MINUTES
HELD ON MARCH 28TH, 2025. | ACTION PERSON | TIME
PRESENT
1. Jane Gichuki– Managing Director
2. Hazel Wananyanga - Operations Manager (CHAIR)
3. Desmond kithinji -Marketing Executive
4. Kelvin Murerwa- IT Manager
5. Diana Arunga – Marketing Executive (RECORDING MEMBER)
6. William Juma- F&B Manager
ABSENT WITH APOLOGY
1. Valentine Wanjiku - Marketing Executive
AGENDA
1. Matters arising from the reading of the previous minutes
2. Events
3. Marketing proposals
4. Marketers reports.
5. AOB.
The meeting commenced with a word of prayer from Diana.
MINUTE 1: MATTERS ARISING.(Reactions to previous minutes)
Reading of the previous minutes done by Desmond.
MD notified Kelvin to include the HDMI purchase in the budget. | Kelvin
It came to our attention that omwasco offices were burnt down thus explains why the have not confirmed their booking.
we told to do a carwash catalogue that we keep adjusting based on changes made for staff to refer also we need to ensure that the head of department is informed. | valentine
marketers were tasked to come up with a kids fun day package rate | marketers
William was tasked to come up with items to push during easter and to present to the heads of departments on Monday | william
kelvin was tasked to revise the previous tour packages and share. | Kelvin
MINUTE 2: EVENTS | all marketers
EASTER:
The easter program finalization was shared and it was agreed that we will have the kid fun day on 20th April 2025, marketers and William were tasked to discuss the entrance fee and finalized details for the fun day . | all marketers and William
Md advised that the best time to visit schools is the 1st to 2nd week of the month since that’s when they are planning for the term. | all marketers
MINUTE 3: MARKETING PROPOSALS
A presentation of the introduction of the sip and paint activity | Diana
A presentation of the family fun day was done | William
MINUTE 4: MARKETERS REPORT
NOTES BY DESMOND:
He mentioned that he had visited Meru for the week.
Places he visited were: Meru polytechnic, St Stephen Catholic church, Consolata primary school, KEMU, ST. Angelic girls, Kaaga girls, Meru TTC, MCK All saints, P.C.E.A Gitoro and Onturiri boys.
He mentioned that he is targeting Karatina and Kagumo for the oncoming week.
He mentioned tentative bookings for next week as follows: Thingithu boys’ school for a team building, Kiiru primary for a hall booking and mbuzi package and KCB which he will share their program by the end of the day.
He mentioned that we need to have tents for hire in case of school camp bookings, since he has a Group planning for August camp.
Year to date- 86,500
Month to date- 44,000
NOTES BY DIANA:
Mentioned that she had visited Muranga for the week.
Places she visited were: K.P.L.C, Muranga lands office, Muranga NEMA, Muranga law courts,County commissioners office, KFS office, AFC offices, MTN sacco,Vidhu ramji academy and vidhu ramji primary.
Mentioned she will be visiting Muranga again for the oncoming week.
Mentioned that food for the hungry are alternative for the week and she will be sharing more details.
Year to date-1,000,850
Month to date- 988,900
NOTES BY KELVIN:
Mentioned he tried football projection at the atrium but it was more visible near the cloakroom wall.
They were to have a discussion with Desmond on a better alternative to air the matches.
He proposed the use of amazon sticks to make the TV smart for ease of live streaming.
He mentioned that on tiktok we are at 1800 +plus followers
He mentioned that Instagram shut down the newly created account an appeal was made on Wednesday they are awaiting feedback.
He mentioned there was an upcoming hotel called Kinyuki Hotel
NOTES BY WILLIAM
He mentioned that we are ready for easter and all contracts have been signed with the concerned parties.
He also mentioned we need to work on duty allocations for easter. | William
NOTES BY THE MANAGING DIRECTOR
She mentioned that marketers are required to be including their target variance and percentage achieved in their weekly reports. | all marketers
She proposed that we be running hotel content on the projected screens when games are on break.
She proposed that we create a frame for the top of the projection area to see if it can block light for ease of projection. | Kelvin & Konez
Advised Kelvin to create a request for boosting socials schedule which he is to share with administration. | Kelvin
Advised we incorporate sip and paint to the health club since it is part of mental wellness.
She advised a training to be conducted on management of the sip and paint activity to other staff and we should have a billing procedure for the activity
She advised marketers to come up with various ways we could align CBC curriculum with our day to day hotel activities | all marketers
She advised a costing to be done to see how we can incorporate Indian koroga at the hotel.
She advised marketers to create a network with marketers so as to be having intel on oncoming activities | all marketers
She observed that our restrooms don’t favor the Muslim community as much thus advised we have several rooms and restrooms with faucets to accommodate this demographic | admin
She advised marketers to pull up their game.
MINUTE 5: AOB:
There being no other business the meeting was closed by a word of prayer by William.
NAME:
SIGN:
DATE:
NAME:
SIGN:
DATE:

## APRIL 11
MARKETING MEETING MINUTES
HELD ON APRIL 11TH, 2025. | ACTION PERSON | TIME
PRESENT
1. Jane Gichuki– Managing Director
2. Hazel Wananyanga - Operations Manager (CHAIR)
3. Desmond kithinji -Marketing Executive
4. Kelvin Murerwa- IT Manager (RECORDING MEMBER)
5. Diana Arunga – Marketing Executive
6. Valentine Wanjiku - Marketing Executive
ABSENT WITH APOLOGY
1. William Juma
AGENDA
1. Matters arising from the reading of the previous minutes
2. Events
3. Marketers reports.
4. AOB.
The meeting commenced with a word of prayer from Diana.
MINUTE 1: MATTERS ARISING.(Reactions to previous minutes)
Reading of the previous minutes done by Desmond.
Kelvin was advised tio use AI images on flyers and avoid guest images. | Kelvin
The recording member for each meeting should state the exact accounts visited by each member.
It was agreed that minutes should be more detailed for effective communication.
It was agreed that we need our own mascot. | Marketers
The team was asked to polish the game drive and bike riding packages. | Marketers
Marketers were tasked to go to churches around and market family fun day event. | Marketers
Kelvin was atasked to post flyers on Nyeri County market place and naromoru online community for a wider reach. | Kelvin
MINUTE 2: EVENTS
EASTER:
MD tasked all marketers to take charge of Easter events preparation to relieve Juma. | Marketers
Valentine reported that all contracts had been signed and deposit paid. She was aked by MD to add contact details of the contact people for ease of follow ups. | Valentine
It was agreed that the mascot should be stationed at the gate in the morning hours to attract guests.
Sip and paint activity was shifted to the front parking lot. Diana to oversee the activity. | Diana
It was agreed that a disclaimer for activities not included in the family fun day rate be put up at the gate
It was agreed that the MC should be invited a few days to the ev ent for briefing. | Kelvin
Kelvin was assigned to manage the band, sound, DJs and the MC.
It was agreed that gate cashiering on 20th should close at 4 pm.
Valentine presented Easter weekend duty allocation. The team was asked to polish the allocation and conduct a staff briefing on Thursday 17th April for seamless execution of the planned events.
MD and Hazel would supervise the event overally.
It was agreed that all marketers should report back on Thursday 17th April for easier planning and coordination of the Easter weekend events.
MINUTE 3: MARKETERS REPORT
NOTES BY DESMOND:
He mentioned that he had visited Nairobi market for the first time.
He visited the following accounts; RSC/CWF AFRICA, SAMSUNG HQ, CREAW KENYA, EACHRIGHT KENYA, RODI KENYA, PELUM KENYA, SOPE KENYA, KENYA RED CROSS HQ, TELEPERFORMANCE KENYA, AFRICA ENTERPRISE CHALLENGES FUND, SAFARICOM, SNV LISTEN KENYA
He mentioned that he is still in communication with Kenya Red Cross Nyeri regional office.
NOTES BY DIANA:
She too had been to Nairobi region for marketing.
Places she visited were: KNHCR, FOOD FOR EDUCATION, ACK HQ, HABITAT FOR HUMANITY KENYA, NATIONAL COUNCIL FOR PERSONS WITH DISABILITY, APDK, WOMEN CHALLENGED TO CHALLENGE, TWIGA CHEMICALS.
NOTES BY KELVIN:
He reported that he had posted flyers on various local online communities and groups but some needed approval by admins to the groups. He would follow up and ensure the posts are approved.
NOTES BY VALENTINE
She reported that she had been in Nairobi for marketing.
She visited the following accounts; CATHOLIC RELIEF SERVICES, CONCERN WORLDWIDE, NATIONAL COUNCIL OF NGOS KENYA, KENYA AIDS CONSORTIUM, CAP YOUTH EMPOWERMENT INSTITUTE WORLDWIDE, YOUTH IKO SOLUTIONS, ACK ST MARKS CHURCH WESTALNDS, & CFAO MOBILITY | Valentine
NOTES BY HR/OM
She reported that all contracts had been signed and depoisits paid in readiness for Easter.
She mentioned that all offs were suspended for the entire Easter holiday.
She reported that there were bookings her and the front office team were following up on for Easter weekend.
NOTES BY THE MANAGING DIRECTOR
She tasked Valentine to folloow up with CFAO Mobility which is a big account and would be great if locked in. | Valentine
She advised Hazel abd marketers to pull up their game since Easter projection on accommodation was not looking good. | Hazel & Marketers
MINUTE 5: AOB:
There being no other business the meeting was closed by a word of prayer by Kelvin
NAME:
SIGN:
DATE:
NAME:
SIGN:
DATE:

## APRIL 25TH
MARKETING MEETING MINUTES
HELD ON APRIL 25TH, 2025. | ACTION PERSON | TIME
PRESENT
1. Hazel Wananyanga - Operations Manager (CHAIR)
2. Desmond kithinji -Marketing Executive
3. Kelvin Murerwa- IT Manager
4. Diana Arunga – Marketing Executive
5. Valentine Wanjiku - Marketing Executive( Recording Member)
6.William Juma-Food and Beverage
IN ATTENDANCE
1.Kones Matahana- Maintenace officer
ABSENT WITH APOLOGY
1.Jane Gichuki- Managing Director
AGENDA
1. Matters arising from the reading of the previous minutes
2.Car Wash Advertising
3. Events
4. Marketers reports.
5. AOB.
The meeting commenced with a word of prayer from Valentine
MINUTE 1: MATTERS ARISING.(Reactions to previous minutes)
Reading of the previous minutes done by Kelvin.
There was advise from MD that we should think about getting our own mascot for future events.Valentine reported that Grace is still following up. | Grace
After the analyzing the Easter event,the DJ Kadz was reported not to have given the hotel the value for it's money.The team was advised that no DJ without any prior perfomance or no evidence of them playing should be called in for mandatory auditions before being contracted.
Desmond also reported that the person that played mascot is also a dj and should be given an opportunity to DJ for future events.
The marketers were advised to stop using abbreviations when reporting their accounts for a better understanding from other members.
Kelvin had a concern that he was not able to record every information from the last meeting and so minute writing was an issue because he was in and out of the meeting.Hazel advised that the person that begins writing the minutes should be the recording member.
Kelvin reported that access to post content on the Naromoru business community,Kieni yetu,Nyeri market place facebook pages had been approved. Desmond advised him to also try reaching out to Nanyuki community page.
MINUTE 2: CAR WASH ADVERTISING
Kones was concerned that the advertising of the car wash had not been done yet.
Valentine was concerned that there was delay of content and that's why the distribution was taking long.
She requested Kelvin to display the car wash flyer for all the members to give their input.
Changes were made and the members suggested that the flyer includes-; Opening time,To use a real time photo of our car wash,inclusion of the location,use of corporate colours,all services to be aligned and a tag line for special discounts for corporates. | Kelvin
Hazel advised Kelvin to redo the flyer, include the catalogue and share it at the end of day to allow time to printing for local activation to be done on Monday after the management meeting. | Kelvin
Members suggested to have a banner or tear drops advertising the car wash.Kelvin was advised to reach out Douglas to find out how much tear drops would cost and seek approval from MD to get some for the car wash. | Kelvin
Desmond suggested that the inclusion of the carwash in the advertising signboard.Kones advised that that would be put in consideration. | Kones
Kones was also concerned that his team was not aggressive enough in the selling of the car wash.The marketers requested to be invited in for a training to the team on how to upsell. | Kones
Kones also suggested to have monthly rates for corporates offering them a 20-30% discount but members advised to first activate the daily wash rates and advised him to think through the monthly rate and advise accordingly. | Kones
MINUTE 3: EVENTS
MINUTE 3: 1 LABOUR DAY
Hazel asked the members to brainstorm on how best we can celebrate labour day as that has never been done before.
Hazel suggested that we have an internal staff appreciation ( Labour day week ) on social media that would happen from 28th April to 1st May.
Kelvin was requested to record videos of staff that would include ;- Name,designation and department and a brief message celebrating the day. | Kelvin
Valentine proposed to have a CSR inititative where we donate meals like Tea & Snacks to the boda boda riders that are placed near the hotel.Hazel advised that would be put in consideration for another event.
She also proposed to have a wall of gratitude where our guests will write messages of appreciation for our staff and for our loyal clients on what makes Jaqanaz Resort feel like home to them.The most exciting answer would be put up for the consideration to win a voucher.
Hazel suggested that we use a styro foam and a frame to make the board.Kones was advised to think about it's logistics and advise the team. | Kones
William suggested we give clients coming in the hotel a gift hamper like what was done for customer service week.The hamper would include a cupcake,sweets and a specialized thankyou note appreciating them. | William
Hazel requested William to suggest a mocktail that would be considered a welcome juice and present it for costing. | William
Desmond also suggested the provision of a notice board near the reception that would be used as an advertising tool to put up upcoming events
MINUTE 3:2 MOTHER'S DAY
Valentine did a presentation of the Mother's day proposal.
Members agreed that out of the activities she presented she should refine the Spa & Accommodation packages and the Mom & Me experience that would involve the sip and paint activity. | Valentine
Kelvin was advised to come up with a social media buzz requesting mothers with the most photos taken at Jaqanaz Resort should post on their social media and tag the hotel's page and the winner would get a voucher that would be decided on. | Kelvin
Kelvin was also advised to run a "Why my mum is the best " contest on social media and the winners would get a voucher for a spa treatment for their mothers. | Kelvin
MINUTE 3:3 CBC ALIGNED ACTIVITIES
Diana did a presentation of the proposal she had previously shared.
The hospitality Industrial Tour exposure came up and was linked as a Career day activity whwere students from different schools come in to tour and explore departments in the hotel.
She was advised by Hazel to come up with packages that would fit the activity and present it for costing to allow for approvals. | Diana
Hazel advised that all other activities will be discussed after the career day packages were rolled out.
Marketers were advised during selling of the packages to be mindful of overbooking students on specfic days and advise the teachers accordingly on bookings.
MINUTE 4: MARKETER'S REPORTS
MINUTE 4: 1 DIANA
She reported that she went to Laikipia whwere she had different appointments and the following were accounts she visited-; • ICRAF-Nanyuki • Illamamusi CFA • Zeltz Foundation • WYSS Nature • Nanyuki Cerials and Produce board • Laikipia Conservancies Association • Big Gulp Beverages LTD
MINUTE 4: 2 VALENTINE
She reported that she had gone to Murang'a county and main focus was other departments in the county Government.The following are some of the departments she visited-; • Trade industrialization & Tourism • Youth Affairs, Culture & Social Services • Education & Technical training • Finance and economic planning • Health & Sanitation
She also reported to have visited the office of Murang'a Youth in coffee initiative that has collaboartions with the county Government and Murang'a farmers cooperative union.
She also got a prequalification 2025-2027 for provision of hotel services and conference facilities and to be delivered before 30th April.
MINUTE 4:3 DESMOND
He reported to have visited Kerugoya and Nyeri and the following are accounts he visited-; • NEMA Kerugoya • KPLC Kerugoya • Kenya Forest Service • Ollin Sacco • County Commissioner Kirinyaga • ACK St Thomas Cathedral • PCEA Curthbert -Nyeri • ACK St Peters Cathedral -Nyeri • KPLC Nyeri
NOTES BY THE OPERATION MANAGER
She encouraged Kelvin to be more proactive in the creating and distributing content for the various events.
MINUTE 5: AOB
There being no AOB the meeting was closed with a word of prayer from Kones.
NAME:
SIGN:
DATE:
NAME:
SIGN:
DATE:

## APRIL 2
MARKETING MEETING MINUTES
HELD ON MAY 2ND, 2025. | ACTION PERSON | TIME
PRESENT
1. Jane Gichuki– Managing Director
2. Hazel Wananyanga - Operations Manager (CHAIR)
3. Desmond kithinji -Marketing Executive
4. Kelvin Murerwa- IT Manager
5. Diana Arunga – Marketing Executive (RECORDING MEMBER)
6. Valentine Wanjiku - Marketing Executive
7.William Juma-Food and Beverage
AGENDA
1. Matters arising from the reading of the previous minutes
2. Events
3. Marketers reports.
4. AOB.
The meeting commenced with a word of prayer from Diana
MINUTE 1: MATTERS ARISING.(Reactions to previous minutes)
Reading of the previous minutes done by Valentine.
Kelvin mentioned that we were not yet approved to post in the Nanyuki community page
It was noted that the Naromoru community page is not as big as the Nyeri one and Kelvin was urged by the MD to keep trying
Kevin reported challenges in sourcing a printing place this explains athe delay in sourcing car wash flyers
Hazel was tasked to follow up on car wash matters, which, though approved, are taking long to be implemented. | Hazel
A CSR activity for the year was proposed. To be discussed: what the activity will be, when, and how. | ALL
Diana proposed that we create our own canvases for the paint activity since it is more affordable, The MD suggested working with the maintenance department on actioning this. She also proposed I be up to date with Grace for purchase so as not to have it as a missing item. | Diana,Grace,Kones
It was proposed that we introduce the wall of gratitude as a permanent feature in Jaqanaz
MD advised that when coming up with proposals, previous turn over vs cost should be a guiding manual. This will help with balancing cost during holidays, such as Mother’s Day. | ALL
Juma proposed the use of mocktails on the menu for special events instead of formulating new creations.
MD mentioned that a board is to be prepared for informatory purposes i.e. daily specials. | MD
It was guided that For any event, Planning and posting should be done 3 weeks prior as an SOP so as to be able to have enough time to reach the audience. | ALL
Kelvin stated that based on the already shared mother’s day buzz online Instagram we got 3 engagements twiter we got 1 engagement
Kevin to action on the Mother’s Day poster by end of day | Kelvin
MINUTE 3: EVENTS
1.CBC
We were advised to include Talk Tour at ksh 300 and commissioning of teachers at 10% was approved
All activities must be prepared and aligned to the CBC curriculum by the various heads of department in Monday advance. | ALL
CBC planning to be completed by Monday.
Proposed components to be included in the CBC package:
Activity Preparation
1. School Engagement Plan
Proposed schedule: engage with two schools per day.
HODs to develop CBC-aligned curriculum.
2.Presentation Materials
HODS to create guides and PowerPoint presentations on the various topics they intend to cover.
Presentations should be visual and tailored to schools.
Target Audience
Desmond proposed to start with local schools.
Marketing Materials
Kelvin to prepare brochures to be used by marketers for the CBC activities by Sunday. | Kelvin
Presentation Standards
HOD advised that all presentations should be properly packaged.
Dress code and presentation style must align to impact students effectively.
MD advised marketers to Look for database on NGO head meetings and trainings since that is a rich source for making conversions | Marketers
And if anyone manages to come across this meetings provision of merchandise will be easily actioned for marketing purposes. | Marketers
Hazel mentioned there is a Kieni east KESSHA meeting on the 17th and we are to receive an invite
MD advised that marketers should be keen when following up with school contact persons due to frequent reshuffles | Marketers
2.MOTHERS DAY
we discussed the mother’s day proposals:
1. Spa & Accommodation
It was proposed that we use the rack rates and discount it to weekend rates. The members suggested that we use the weekend rates . it was also advised that for the winning category we give accommodation on bed only basis to the mum to maximize on purchase from clients.
2. Mom & Me Experience
This entails guided exercises by our health club team.
The karaoke activity is to create an engagement between mothers and their children to be coordinated internally by Juma.
Kelvin was tasked to inform us about sound and microphones to be used on the said date.
It was noted that Brian Mbotela is also a DJ and is be engaged to DJ on that day. Kelvin and William to give feedback.
3. Social Media contest
Kelvin should run a “Why my mum is the best” contest on social media and the selected winners would win their mothers a Steam or Sauna voucher.
He should also put a tag requesting mothers with the most photos at Jaqanaz on different days to post on social media and tag the page. The mother with the most photos will win an accommodation voucher.
Kelvin was advised to be proactive in the creating of the content to allow ample planning time.
The purchase of pink flower bouquet and an appreciation note that will be presented to the mothers together with the bills.
MINUTE 4: MARKETER'S REPORTS
MINUTE 4: 1 DIANA
DORMANT ACCOUNTS
She reported that she is following up on the accounts bellow:MEWASS, Marie Stope Kenya,GATUNDU LAW COURTS
KIRINYAGA WEST KESSHA
Muranga Law Court
ACCOUNTS VISITED
She reported that the following were accounts she visited-;
First choice layers depot
National cereals and produce board
Kerugoya law courts
Kukena sacco
Grace breakthrough
Agricultural sector development and support program
MCA Erick Murithi's office
The peoples church and the kingdom school
MINUTE 4: 2 VALENTINE
She reported that she is following up on the accounts bellow:USAID,NHIF (Nyeri & Nanyuki),Nanyuki water,Golden green properties,Gataragwa Girls,Nyeri hillstead, Eagle management consultants
ACCOUNTS VISITED
She reported that she had visited the accounts bellow:
Pharmacy and poisons board-nyeri
Energy and petroleum regulatory authority-nyeri
IPOA nyeri
One acre fund-nyeri
KEPHIS- nyeri
SHIF -nyeri
Nyeri hill farm-mathari
MINUTE 4:3 DESMOND
DORMANT ACCOUNTS
He reported that she is following up on the accounts bellow:Each rights Kenya,Rodi Kenya,Listen project,AMREF and Michuki training institute
ACCOUNTS VISITED
He reported to have visited the following accounts visited-; | Marketers
KMTC - OTHAYA
Iriaini Tea Factory
Chinga Tea Factory
ACK ST James Kanyange
Wanainchi DT Sacco
CIC Insurance -Nyeri
Kenya Red Cross - Nyeri
Caritas MFB Bank-Nyeri
Water Resources Authority
Marketers were tasked to come up with ways of rejuvenating dormant accounts
Kelvin mentioned he got an inquiry from tik tok, Namu travels group which he forwarded to the Front desk team.
William mentioned that he is following up with AG nutrition on accommodation towards the end of the month
Hazel mentioned that she had advised the AG nutrition leaders to format their messages and reminders stating Jaqanaz as the venue.
MD advised William since he is the one in communication with AG nutrition he should do more of texting as a form of written agreement as compared to making calls
NOTES BY THE MANAGING DIRECTOR
She advised Hazel to do an appreciation letter to the performeter group.
during the MSM staff need to be informed of the good work done
marketers to be projecting on their performance moving forward.
MD advised marketers to help Kelvin with content creation.
kelvin should have a3 days for flyer production, feedback by HODS to be given in 12 hrs. then I day allocated for printing thus a total of 5 days before posting and printing
NOTES BY THE OPERATION MANAGER
Desmond and William were commended fort the good job in welcoming and orienting the performeter group, she also advised on the importance of guest profiling so as to better their stay
MINUTE 5: AOB
There being no AOB the meeting was closed with a word of prayer from Hazel .
NAME:
SIGN:
DATE:
NAME:
SIGN:
DATE:

## MAY 9
MARKETING MEETING MINUTES
HELD ON MAY 09TH, 2025. | ACTION PERSON | TIME
PRESENT
1. Hazel Wananyanga - Operations Manager (CHAIR)
2. Desmond kithinji -Marketing Executive (RECORDING MEMBER)
3. Kelvin Murerwa- IT Manager
4. Valentine Wanjiku - Marketing Executive
5.William Juma-Food and Beverage
ABSENT WITH APOLOGY
1.Jane Gichuki- Managing Director
2. Diana Arunga – Marketing Executive
AGENDA
1. Matters arising from the reading of the previous minutes
2. Events
3. Marketers reports.
4. AOB.
The meeting commenced with a word of prayer from Desmond
MINUTE 1: MATTERS ARISING.(Reactions to previous minutes)
Reading of the previous minutes done by Valentine.
Kelvin mentioned that was Jaqanaz approved to post in the Nyeri community page
Kelvin mentioned will follow up on progress for canvases as Kones in on short leave | Kelvin
Kelvin Mentinoned they distributed Car wash around Narumoru Center and public had good reaction.
Kelvin to finalize arrangement with Dj Brienk for Mothers Day music selection. | Kelvin
Valentine was tasked to coordinate all preparation for Mothers Day program. | Valentine
MINUTE 3: EVENTS
1.MOTHERS DAY
Mother’s day program was tasked to Valentine with assist of William.
They were to come with a team to play live Karaoke during the day with help of staffs to be coordinated internally
Kelvin reported he was done with Appreciations video with help of staffs to wish all mothers a Happy Mothers Day
2. Madaraka Day
Juma took team through year calender next upcoming event being Madaraka Day on 1st June 2025
Hazel mentioned we kelvin to finish up with Madaraka Day Flyer.
Proposed madaraka day rate to be our rack rates and to be on flyer.
Valentine was tasked to come up with proposed best DJ to play Rhumba on the day or engage DJ Brienk on same.
MINUTE 4: MARKETER'S REPORTS
MINUTE 4: 1 VALENTINE
Mentioned she had visited following accounts;
ACCOUNTS VISITED
Pmi Church-Nyeri
Rware High
King'ong'o Parish
Nyeri Good Shephered
Ministry Of Agriculture & Livestock
Biashara Sacco-Nyeri
Nyewasco
Nyeri Law Courts
Mathaithi Parish-Karatina
MINUTE 4:2 DESMOND
Mentioned he had visited following accounts;
ACCOUNTS VISITED
St Angelic Girls-Meru
Pcea Gitoro - Meru
Kaaga Girls
Meru School
Meru Teachers College
Karumo Technical Training Institute
Bishop Lawi Imathiu Sec Sch
Amref Health Africa
Chinga Boys High School
Othaya Boys
Pcea Icuga Church
Karemeno Secondary School
NOTES BY THE JUMA
He mentioned on complaint on Lamb meat affected one member of Rainforest Alliance, He advised marketers to ask guest on special needs to avoid such cases.
Requested if we can get Chevon (Goat meat) as premium option as a guest needs specific.
He commended good job marketers are doing,also to push more business from school and churches.
NOTES BY THE OPERATION MANAGER
Mentioned madaraka flyer to be done early and be pushed on our socials
She advised that weekend having low profit and tasked Kelvin to do a proposal guiding on rates to be used,as weekend we have been getting a lot of guest and selling on weekend rates is low.
emphasized during booking taking to take special requirement to avoid complains from groups and individuals | Kelvin
Reaction on introducing royalty program,tasked Desmond to come with a proposal | Desmond
Mentioned will guide on rolling out Christmas program and flyer
Will update on two events to be held on 17th and 30th May.
MINUTE 5: AOB
There being no AOB the meeting was closed with a word of prayer from Valentine .
NAME:
SIGN:
DATE:
NAME:
SIGN:
DATE:

## MAY 16TH
MARKETING MEETING MINUTES
HELD ON MAY 16TH, 2025. | ACTION PERSON | TIME
PRESENT
1. Hazel Wananyanga - Operations Manager (CHAIR)
2. Desmond kithinji -Marketing Executive
3. Valentine Wanjiku - Marketing Executive (RECORDING MEMBER)
4.William Juma-Food and Beverage
IN ATTENDANCE
1.Jane Gichuki- Managing Director
ABSENT WITH APOLOGY
1.Kelvin Murerwa-IT Manager
AGENDA
1. Matters arising from the reading of the previous minutes
2.Events
3. High Season discounts /Weekend offer rates
4.Proposals
5. Marketers Reports
6.Conversions
7.AOB
The meeting commenced with a word of prayer from Valentine
MINUTE 1: MATTERS ARISING.(Reactions to previous minutes)
Reading of the previous minutes done by Desmond.
Kelvin was requested to updae the car wash flyer to add other types of cars for all clientele inclusion. | Kelvin
Diana was requested to follow up with Kones and Gituku and give an update of the painting canvases. | Diana
Hazel advised that during booking taking,all marketers should handle the bookers of the groups hands on so as to get any persons with special dietary restrictions and people who are abled differently to avoid the inconveniencing of the guests and the hotel.-This was in connection to the Rainforest Alliance group. | Marketers
Hazel was concerned that the weekend having low profits and tasked Kelvin to do a proposal guiding on rates to be used,as weekend we have been getting a lot of guests and selling on weekend rates is low. | Kelvin( Pending from previous meeting)
Hazel gave an update of the events that were coming up and advised that 17TH May 2025 Amani clubs Rware High Desmond 25th May 2025 Nanyuki golf tournament Nanyuki Sports Club Valentine 31st May 2025 Teacher’s welfare Giachuma Diana & Desmond | Marketers
MINUTE 2: EVENTS
Minute 2:1.Madaraka Day (1st June 2025)
Valentine briefed the team that Dj Braniek was going to be the dj of the day.She mentioned she had requested him to come up with a Rhumba playlist and shre with the team for approval.However,the team advised that he is called for an audition one weekend. | Valentine
Valentine requested that we get a designer from outside now that Kelvin was indisposed but MD requested that she asks Kelvin to work on it first and give feedback for presentation on Monday. | Kelvin
William reported that the menu for the day will be alacarte so as to enable monitor the new food prices that were introduced.
William reported he had come up with a staffs dresscode i.e Service team & housekeeping to wear black and white with a touch of the Kenyan flag.
Décor for the hotel will be done with the kenyan flag themed shukas and hay as it's normally done.
Diana suggested that Kelvin puts up a projection of the Kenyan history in the atriumto commemorate the day . | Kelvin
William was tasked to come up with a program and share in the next meeting. | William
Minute 2.2: Father's day (15th June)
William was tasked to come up with an activity for the day. | William
Kelvin should come up with content.-Flyer | Kelvin
Minute 2.3: Mazingira Day (5th June)
Diana reported that there will be no activities in Naromoru as had been planned.The group will clean Nanyuki River.
MD mentioned that on the same day there the KFS normally bring lunch to the hotel and Desmond was advised to follow up with Baba George to get an insight on the activities that will be happening in Naromoru. | Desmond
4.Christmas Day(25th December 2025)
Hazel advised that F & B in connection with Kitchen to come up with themed buffet menus. | William
After the menus are shared,the Christmas committee will sit and come up with a program for the holiday.
The marketers will come up with room rates for the holiday thereafter that will be the main point of sale in the upcoming holidays expo that will be held in KICC in August 2025. | Marketers
The members were also encouraged to come up with décor ideas for the holiday.
All the content should be completed by 15th June 2025.
MINUTE 3: HIGH SEASON DISCOUNTS/WEEKEND RATES
Members were concerned that the hotel was giving too many discounts mostly during the holidays.
Hazel suggested that we use high season rates during the holidays.
MD advised that Grace should provide data from 2022-2024 bookings and how much of the discounts have been given versus revenue achieved. | Grace & Desmond
She also advised Desmond and Hazel to follow up and the data should be shared for discussion during the next meeting. | Desmond & Hazel
Hazel was also concerned that the weekend was making little to no sales because of the effect of the weekend offer rates and she advised that the rates are alternated with the rack rates.
MD advised that Daniel does the room costing for 4,000 and 4,500 to determine the viability of the alternation of rates.
Front office was also advised to analyze sales for the last 2-3 years and Hazel should do a proposal to present to the board during their meeting on Saturday. | Hazel
MINUTE 4:PROPOSALS LOYALTY PROGRAM
MINUTE 4:1 LOYALTY PROGRAM
Desmond presented the loyalty program with the below objectives-;
1.Increase repeat bookings and direct reservations.
2.Build customer loyalty and brand affinity.
3.Encourage utilization of resort amenities including the Health Club, accommodation,restaurant, and conference facilities.
Hazel proposed that the program could apply to the group bookers.
It was advised that the hotel system was not been used efficiently and a back up should be incorporated and training done for Front office & accounts
It was advised that it should be categorized by individuals via data -Accommodation & ala carte clients.
MD advised that Desmond thinks through the strengths and weaknesses of the proposal shared.-Control measures
Desmond should work on it before Christmas and any incentives to be given to guests should be within the facility and to be addressed to the need of the client.
He was advised to think through how the whole program should run and advise during the next meeting. | Desmond
MINUTE 5:MARKETERS REPORTS
Minute 5:1 Valentine
She reported that she had visited the following accounts-;
M.O.H-Laikipia county Nutritionist-Nanyuki
NOTHERN RANGELAND TRUST-Nanyuki
KENYA INSTITUTE OF CURRICULUM DEVELOPMENT-Nairobi
POPULATION COUNCIL -IDEAS EVIDENCE IMPACT HEALTH-Nairobi
NOVO NORDISK-Nairobi
YOUNG LIFE KENYA-Nairobi
GROOTS-KENYA-Nairobi
COMPASSION INTERNATIONAL KENYA-Nairobi
NASCOP-Nairobi
KENYA MEDICAL RESEARCH INSTITUTE HQ-Nairobi
TB PROGRAMME-Nairobi
MALARIA PROGRAMME-Nairobi
She mentioned that most of the accounts she visited were previously visited by GM and it was easy to re-introduce the hotel and new rates to the groups which most are lead prospects.
MINUTES 5:2 DESMOND
ACCOUNTS VISITED
THINGITHU BOYS SECONDARY SCHOOL- NANYUKI
P.C.E.A BETHANY CHURCH-NANYUKI
P.C.E.A BARAKA CHURCH-NANYUKI
Centre for Training and Integrated Research in ASAL Development-CETRAD
BISHOP GATIMU NGANDU GIRLS
MATHIRA TECHNICAL AND VOCATIONAL COLLEGE
P.C.E.A KIRIKO CHURCH-KARATINA
TUMUTUMU GIRLS SCHOOL
PCEA TUMUTUMU CHURCH/OFFICE
PCEA TUMUTUMU HOSPITAL
CAP-Youth Empowerment Institute/STEM Education for Empowerment Project (STEEP).
KENYA RED CROSS CENTRAL REGION OFFICE
He mentioned that he has a tentative from Thingithu boys for Mbuzi package.
Bishop Lawi is also interested to bring prefects.
Karumo teachers is also interested in Mbuzi package for the staff welfare in June.
Minute 5.3 DIANA
Accounts visited-;
PRIME START ACADEMY
SKY LIMIT ACADEMY
GAKUU SECONDARY
ST TRIZAH GIRLS
JOY MILLERS
ACK ST PAUL
KICOWASCO
WRA
ST. JOSEPPH
She also mentioned that Nakuru is a big market that needs to be explored.
She mentioned that the International schools she visited mainly bring the students to Tafaria Castle and Chaka ranch because their main focus is activities for the students.
MINUTE 6: CONVERSIONS
Desmond mentioned that he had achieved
Revenue achieved to date-KES 195,450 out of KES 2,267,500 at 8.6%
Diana reported that she had achieved
Revenue achieved to date-KES 1,195,140 out of KES 4,367,500 at 27.36%
Valentine reported that she had achieved
Revenue achieved to date-KES 2,904,375 out of KES 8,304,000 at 34.9%
MD advised the marketers to keep track of all the prequalification documents that are filled to avoid missing out on business. | Marketers
Hazel was tasked to come up with a program of re-introducing targets for all the HODs and share to take effect in June. | Hazel
MD advised that each marketer from the data shared should focus on specific accounts that are strong business holds.
Marketers to track all their accounts -Tentative & Converted accounts. They should come up with a business mix of their own that would include a pie chart that would show all the translations. | Marketers
Marketers were advised to create time out of the marketing days to do follow ups on their accounts so as to determine what accounts that they should keep pursuing and include data of accounts in their marketing reports. | Marketers
The below accounts were designated to the marketers;-
Wananchi Sacco,Tower Sacco,2nk Sacco | Desmond
Fortune Sacco,Mentor Sacco,Biashara sacco | Valentine
Kidapu Sacco, | Diana
MINUTE 7: AOB
MD revoked that the selling of hot water in the hotel from feedback she got from a client and the feedback that has been given from other clients within the hotel.She however advised members to think of the reason why selling hot water was introduced.
She was concerned that clients would now start idling and Valentine proposed a table charge of 500 pp for those that are not willing to spend.
She encourged all the members to translate business.
NAME:
SIGN:
DATE:
NAME:
SIGN:
DATE:

## MAY 24TH
MARKETING MEETING MINUTES
HELD ON 24TH MAY, 2025. | ACTION PERSON | TIME
PRESENT
1. Hazel Wananyanga - Operations Manager (CHAIR)
2. Desmond kithinji -Marketing Executive
3. Valentine Wanjiku - Marketing Executive
4. Diana Arunga – Marketing Executive (RECORDING MEMBER)
5. William Juma- F&B Manager
ABSENT
1. Kelvin Murerwa- IT Manager
ABSENT WITH APOLOGY
1. Jane Gichuki- Managing Director
AGENDA
1. Matters arising from the reading of the previous minutes
2. Events
3. Marketing proposals
4. Marketers reports.
5. AOB.
The meeting commenced with a word of prayer from Diana.
MINUTE 1: MATTERS ARISING.(Reactions to previous minutes)
Reading of the previous minutes done by Diana.
Desmond gave us an update on his visit to Rware High (Amani Club Association) he got to reach 150 teachers which he will be sharing with the fellow marketers, and was given a platform to sell the CBC program, which was well received. | Desmond
the laikipia forum tourism expo to be held on 3rd may 2025 will be attended by marketers | marketers
Rack rates to be used for 1st June 2025(Madaraka day)
In preparation for madaraka the front desk operators and service team are given priority in regards to flag themed attire, and HODS to wear their black and red tshirts
It was noted that we require the Kenyan flag, Laikipia county flag and a Jaqanaz resort flag to honour public holidays
In alignment to Madaraka a research on videos to air connected to madaraka day. | Kelvin & Desmond
Desmond was tasked to see if we can acquire the Laikipia county flag | Desmond
it was stated that all H.O.Ds are required to attend their respective meetings and in the case meetings align with their off days they should make necessary adjustments . Ref: Kelvin | ALL
Tasked to talk to baba Georgie from KFS in regards to mazingira day | Desmond
Sharing of the christmas menu to be done by 25th may 2025 | William
It was stated that Groots kenya and K.C.B are direct accounts
It was advised that we be using MR.Musili instead of the GM during minute writing | All
MINUTE 3: MARKETING PROPOSALS
1. A presentation of the Jaqanaz CBC funday | Valentine
key points:
marketers were tasked not to forget to mention the 10% commission to teachers.
proposed rates are as follows: 400 activity without food, 700 activity with food.
caring of food stuff to the resort is discouraged.
The Operations Manager tasked Marketers to come up with the exact dates for the proposed fun day. | All
she also tasked marketers to research on items and activities for the fun day | All
she also tasked marketers to keep tabs with Owen to help in pulling numbers for the fun day with a 10% commission offer | All
It was mentioned that we could introduce the funday to teachers at Giachuma (KESSHA) | All
in alignment to the activity line up Diana proposed Birdie mascot makers to make our own mascot.
2. Loyalty program presentation | Desmond
Desmond was advised to work with accommodation and dining in terms of awarding points
He was tasked to inquire on integration of mpesa to hotelplus can be done | Desmond
He was also tasked to research on possible pros and cons for the proposed loyalty program
MINUTE 4: MARKETERS REPORT
NOTES BY DESMOND:
Places he visited were:
KMTC -OTHAYA
ACK ST PAUL CHURCH- OTHAYA
A.I.P.C.E.A- OTHAYA
WANAINCHI DT SACCO- OTHAYA
P.C.E.A CHURCH- OTHAYA
ALMASI BEVERAGE LIMITED- COCA COLA
2NK SACCO
KENYA RED CROSS CENTRAL REGION OFFICE
NSSF NANYUKI
KRA NANYUKIACCOUNT
KMTC -OTHAYA
ACK ST PAUL CHURCH- OTHAYA
A.I.P.C.E.A- OTHAYA
WANAINCHI DT SACCO- OTHAYA
P.C.E.A CHURCH- OTHAYA
ALMASI BEVERAGE LIMITED- COCA COLA
2NK SACCO
KENYA RED CROSS CENTRAL REGION OFFICE
NSSF NANYUKI
KRA NANYUKI
NOTES BY VALENTINE:
THE NUCLEAR POWER AND ENERGY AGENCY-NAIROBI
KENYA INSTITUTE FOR PUBLIC POLICY RESEARCH AND ANALYSIS (KIPPRA)-NAIROBI
HIGHER EDUCATIONS LOAN BOARD (HELB)-NAIROBI
KENYA ELECTRICITY TRANSIMISSION COMPANY LIMITED (KETRACO)-NAIROBI
AQUACULTURE BUSINESS DEVELOPMENT PROGRAMME ( ABDP)-NYERI
TETU ABERDARE WATER AND SANITIZATION COMPANY (TEAWASCO)
DIRECT LINE ASSURANCE-NYERI
INDEPENDENT POLICING OVERSIGHT AUTHORITY( IPOA) NYERI
MONARCH INSURANCE-NYERI
NOTES BY DIANA:
Places she visited were:
National Drought Management Authority
Huduma Kenya Secretariat
African Organization For Standardization (ARSO)
Talos Energy For The World
Premier Safaris
SIYB Association of Kenya
Capital Strategies K Limited
Turbi Energy
Kidapu SaccoKiambu
Twiga chemicals
Desmond mentioned that he had achieved
Revenue achieved to date-KES 195,450 out of KES 2,267,500 at 8.6%
Diana reported that she had achieved
Revenue achieved to date-KES 1,538,480
out of KES 4,367,500 at 35.22%
PROSPECTS FOR THE WEEK
William mentioned he had Jane Gatwiri for a birthday booking on31st may.
notes by the operations Manager :
She tasked marketers to come up with timelines for assessment to enable her to create a performance matrix.
she advised marketers to focus on conversions | marketes
She assigned various tender awards for follow up, jacaranda health solution to the front desk, Kenya power pension fund-Diana, Action against hunger- Desmond, Communication authority- valentine
She tasked marketers to inquire on expos: | all marketers
organizer contacts, what we intend to show case, décor to use and merchandise | all marketers | 15th june
MINUTE 5: AOB:
Desmond thanked Hazel for the redcross tender support
valentine encouraged team work
NAME:
SIGN:
DATE:
NAME:
SIGN:
DATE:

## JUNE 7TH
MARKETING MEETING MINUTES
HELD ON JUNE 7th, 2025 (9:30AM - 11:50 PM) | ACTION PERSON | TIME
PRESENT
1. Hazel Wananyanga - Operations Manager (CHAIR)
2. Kelvin Murerwa - IT Manager
3. Valentine Wanjiku - Marketing Executive(Recording member)
4. Diana Arunga – Marketing Executive
5. William Juma- F&B Manager
ABSENT WITH APOLOGY
1. Desmond Kithinji - Marketing Executive
IN ATTENDANCE
1.Jane Gichuki-Managing Director
2.Grace Huho-Accountant
AGENDA
1. Matters arising from the reading of the previous minutes
2. Events
3. Marketer's commision
4. Marketers reports.
5. AOB.
The meeting commenced at 0900hrs with a word of prayer from Valentine.
MINUTE 1: MATTERS ARISING.(Reactions to previous minutes)
Reading of the previous minutes done by Kelvin.
Valentine reported Welfare official had a meeting and give them task to share place to give CSR.She will update on same | VA
Room rates will be standardised to avoid selling the weekend rates after the concern on low revenue returns on the weekends.Effect takes place on 1st July 2025. Hazel to also brief the Reservations desk | Hazel
Kelvin was asked to find out the cost of implementing M-Pesa intergration into the PMS and provide a detailed and written research data | Kelvin
Desmond to give updates on his pending tasks in the next meeting and that would include-Loyalty program | Desmond
MD raised the concern about a member missing 2 consecutive meetings.Hazel was asked to advise the team in the next meeting as this was in regard to Desmond missing 2 meetings. | Hazel
As a report that Valentine had given on the attendance on the Laikipia Tourism Expo 2025 in Nanyuki,Tour operators asking for 15%-30% commision,MD advised that the tour operators are advised to upsell our rack rate and get commissions after tax deductions.
MINUTE 2: EVENTS(Father's Day )
Kelvin reported that he had already shared the flyer in all social media platforms.
He also reported that he was going to shoot video content in regards to the event. | Kelvin
Hazel should work on contracting the one man guitar at a price of 4k that was agreed on by the members and approved by the MD.She was advised to request him to lower his rate in return for a weekly/Monthly contract to play on weekends. | Hazel
It was also clarified that Dj Braniek gets paid 3k after every perfomance.It was also been reported that his clients were asking for weekly perfomances in the hotel and MD advised that it's an activity that can be implemented but William and Hazel need to sit and agree on logistics and advise accordingly. | Hazel & William
MINUTE 2:1 EVENTS(Christmas Day )
As the event is still in it's planning stages,MD advised members to sit through the meeting and be involved in the presentation after finalizing. | William
Hazel advised to have the meeting on Tuesday,10th June 2025 at 0930hrs.
MINUTE 2:3 EVENTS(CSR )
Hazel reported that she was hoping for a hospice visit from the staff to be in collaboration with Action For Hunger(Diana's Group) to also enable conversion and breakthrough with the group.
MD advised that any CSR activity that should be agreed upon should not be an activity that we should expect anything in return in terms of return of Investment.It should be purely a charity event.
Welfare chairperson in collaboration with Admin office were advised to come up with a plan and advise in due time. | Valentine & Hazel
MINUTE 3: MARKETER'S COMMISSION
Grace did a presentation on how the commissioning totals were done using the commissioning matrix bundle.
Ksh | Commission
0-200,000 | 0.5%
200001- 500,000 | 1%
500001-1 million | 1.5%
1000001 -2 million | 2%
2 million and above | 2.5%
She also presented the food costs for Taifa Sacco,Capital Sacco and Pastor Jeff's group that showed that the food cost was at 35% instead of the normal 22% and that was been caused by the low and discounted rates for the groups.
She advised the marketers to try and sell the rack rates or even upsell to allow maximization and balance of the food cost.This will allow the F& B,Kitchen,housekeeping optimize on customer satisfaction and experience. | Marketers
She also shared the concern that is low rates were given to clients this would hinder the commissioning totals for the marketer's,groups and also the maintenance cost of the groups.
She advised the marketers to avoid giving large discounts and underselling the packages.
MD advised that the transitional accounts should be identified and listed by name and presented in the next meeting. | Hazel
She advised that such accounts should be allowed to sell in the current rate they are at but will slowly be introduced to the rack rates by their respective account managers. | Marketers
MD posed the question on when the marketer's commissions should be paid and it was proposed and approved to be paid after every 3 months.
She advised Grace to pay all commission dues that were owed to marketers. | Grace
The co sharing policy is at 60/40 between the account managera nd convertor of business.
MINUTE 4: CONFERENCE RATES
From the commissioning matrix there was a concern on the conferencing rates on them being too high.
Valentine proposed to separate the accommodation aspect from the conference rates.Both room and conference to be charged seperately.
It was proposed and approved that the residential conference single occupancy is charged at 9,500 and if need be for discounts to be sold at 9,000 minimum.
Grace raised the concern to do away with church and school packages but MD advised due to their capitation rates should be 8,500 single occupancy and 8,000 sharing.
Marketers were advised to encourage the bookers to load up to the rates so as to get the account maintenace fees if required. | Marketers
MINUTE 4: MARKETERS REPORT
Chair advised that Desmond's reports be postponed to the next meeting.
NOTES BY VALENTINE:
Northern Rangelands Trust(NRT)
World Vision
Action Aid
Mercy Corps
BOMA Project
County Government of Isiolo
Isiolo Gender Watch
Water Resource Authority Isiolo
Isiolo Water & Sewerage Authority
WASO Trust land
Star Of Hope Association
Caritas Isiolo
She reported that Revenue achieved year to date: KES 2,987,775 which is 36% of her yearly target.
She reported that she was now doing follow up of her accounts she has visited since trying to balance out on accounts that she should still explore.
She reported that there were no dietary concerns for the upcoming Taifa sacco groups.She also reported that she had talked to Mathenge about the excess groups that would use Heron hall because of projection but was advised by MD to table the idea of the extra group bringing their projector.
She requested Kelvin to look at the emails that she had sent to companies but had bounced. | Kelvin
NOTES BY DIANA:
Laikipia conservercies association
Nature Kenya
MKWEP
Mount Kenya Trust
Flora & Fauna
Seedpro (Agriculture)
Revenue achieved year to date: KES 1,534,890 which is 38.2% of her yearly target.
Key Prospect This Week:
Madam Peninnah's group- Synod JCTM
70 pax 2 mbuzi ,8 local chicken, package and AM tea confirmed for 7th June2025
M.C.K ST . PAUL
30 pax 1 mbuzi ,4local chicken, package and AM tea tentative for 14th June2025
She reported that there was a pitch she was going to present on the 12th and 13th to the KTDA office in Meru and there was content she was coming up with and was going to share with OM & MD for approvals. | Diana
She projected different designs of booth décor for the expo from Homeland events.Hazel advised that she should get different quotations from different suppliers and share in the next meeting. | Diana
NOTES BY WILLIAM
He reported that he had sold the Pergola Experience to Desmond's inhouse guests who were very happy and was advised to come up with the product and share it with accounts office for costing.
MD commended the initiative and encourgaed the members to sell the product.She advised that she was now going to take over the product in terms of construction and it's logistics.
NOTES BY THE OPERATIONS MANAGER (CHAIR)
She advised members to get quotation from atleast 3 suppliers to help in comparisons before settling for any. | Diana & Kelvin
She advised Valentine to reach out to the organizers of the Magical Kenya expo to get a better understanding of the booths and any detail that would help in the preparation of the team. | Valentine
She reported she was going to advise on speakers selected for the Men's mental Health program for the male staff. | Hazel
She advised to have the Christmas meeting on Tuesday ( 10th June 2025)
NOTES BY MANAGING DIRECTOR
She encouraged all the members to push to convert business as the month and year was not looking very promising in terms of revenue.
She requested Hazel to also ask the reservations desk to do a chart analysis like the one the marketers had presented of all the direct accounts converted. | Hazel
She encouraged the marketers to do a SWOT Analysis of their converted pie charts. | Marketers
MINUTE 5: AOB:
The meeting ended at 11:50 am.
PROPOSER
NAME: ______________________________________ SIGN _______________________
DATE:
SECONDER
NAME: ______________________________________ SIGN _______________________
DATE:
SECRETARY
NAME: ______________________________________ SIGN _______________________
DATE:

## JUNE 14TH
MARKETING MEETING MINUTES
HELD ON JUNE 14th, 2025 (9:30AM - 01:00 PM) | ACTION PERSON | TIME
PRESENT
1. Hazel Wananyanga - Operations Manager (CHAIR)
2. Desmond Kithinji - Marketing Executive(Recording member)
3. Kelvin Murerwa - IT Manager
4. Valentine Wanjiku - Marketing Executive
5. Diana Arunga – Marketing Executive
6. William Juma- F&B Manager
7.George Ndegwa- F.O supervisor
IN ATTENDANCE
1.Jane Gichuki-Managing Director
AGENDA
1. Matters arising from the reading of the previous minutes
2. Events
3. Marketers reports.
5. AOB.
The meeting commenced at 0932hrs with a word of prayer from Juma.
MINUTE 1: MATTERS ARISING.(Reactions to previous minutes)
Reading of the previous minutes done by Valentine.
Mentioned Dj Braiek to perform on father days on 15th June 2025,Theme being Rumba on the day. | Kelvin
Valentine reported Welfare official had a meeting and give them task to share place to give CSR.She will update on same | Valentine
Kelvin to follow up on implementing M-Pesa intergration into the PMS. | Kelvin
Valentine reported she is following on Magical Expo and she will give update on same. | Valentine
She mentioned atleast member should not miss for 2 consecutive meetings. | Hazel
MINUTE 2: EVENTS(Father's Day )
Kelvin reported the flyer in all social media platforms.
He also reported that he was going to shoot video content in regards to the event. | Kelvin
It was agreed Dj Brainek to perform over weekend on Father Day.Mainly he should play Rhumba as it was theme of the day
Marketer were tasked to come with a Fathers day surprise message of the day | Marketers
MINUTE 2:1 EVENTS(Christmas Day )
Hazel advised to have the meeting on Tuesday,17th June 2025 at 0900hrs. | Hazel
To discuss on Christmas rates.
MINUTE 2:3 EVENTS(CSR )
Valentine reported Welfare official had a meeting and give them task to share place to give CSR.She will update on same | Valentine
MINUTE 4: MARKETERS REPORT
NOTES BY DESMOND:
P.C.E.A - KARATINA TOWNSHIP
P.C.E.A ITIATI MAGUTU PARSH - KARATINA
KARATINA SUB-COUNTY HOSPITAL
MATHIRA WATER & SANITATION COMPANY LTD
P.C.E.A MAHIGA PARISH-OTHAYA
P.C.E.A OTHAYA TOWNSHIP CHURCH
KMTC -OTHAYA
TOWER SACCO- NYERI
NEW FORTIS SACCO NYERI
P.C.E.A ST PAUL ACADEMY - NARUMORU
He reported that Revenue achieved year to date: KES 227,950 which is 10.1% of His yearly target.
Reported following on group deposit to lock booking and pushing to lead groups for conversions.
Presented Jaqanaz Loyalty Program.MD adviced him to think about and share on early August find how it will work. So we can enroll before Christmas | DESMOND
NOTES BY VALENTINE:
She reported that Revenue achieved year to date: KES 2,987,775 which is 36% of her yearly target.
She reported was to attend on MICE EXPO at sarit center but she was caught in demo were across CBD which deemed unsafe to get to centre
She reported working on ActionAid RFQ
Valentine reported she is following on Magical Expo and she will give update on same from organizers.
Key Prospect This Week:
Reported Taifa sacco will check in 14 pax
NOTES BY DIANA:
Mwichuiri Secondary
Capital Sacco
CIC Insuarance
kionyo tea factory
Yetu sacco
Times U DT Sacco
Weru tea factory
Revenue achieved year to date: KES 1,714,890 which is 39.26% of her yearly target.
Key Prospects:
M.C.K ST . PAUL
25pax, 1 mbuzi package and AM tea tentative for 14th June2025
Laikipia Conservancies Association:
Ol Pajeta conservancy accommodation on half board basis 28 pax on 15th June,2025.
She reported food for the Hungry will be coming on 23rd - 27th. | Diana
Mentioned photoshoot disclaimer should be designed and be placed on several point. | Kelvin
She took on Jaqanaz presention she pitched to the KTDA office,MD asked team to refine and add more picture to create master markerting presentation for marketing and pitching | Marketers
Mentioned now competency-based curriculum(CBC) have changed to Competency-Based Education (CBE) Training
NOTES BY KELVIN
He reported working on design on Expo counter and layout he will updated on finding from source.
Mentioned marketer to check on I&M Bank Nanyuki Branch. | Marketers
He mentioned working on refining disclaimer notice.
Mentioned will polish Fun day Flyer by end of the day and to be shared.
NOTES BY WILLIAM
He breifly took team on Christmas rate.
He mentioned more on rates will be discussed on scheduled meeting on Tuesday,17th June 2025 at 0900hrs
NOTES BY THE OPERATIONS MANAGER (CHAIR)
Hazel advised to have the meeting on Tuesday,17th June 2025 at 0900hrs.To discuss on Christmas rates | Marketers
She took team on Group bookings evaluation & Prioritization process to avoid conflicts arising from overlapping group bookings or multiple groups competing for the same dates. This approach is aimed at: 1.Enhancing clarity and transparency in booking decisions 2.Ensuring we prioritize groups based on return on investment and operational capacity 3.Fostering better communication and collaboration across departments She will share same on email outlining the evaluation criteria and procedures | Marketers
She insisted to all marketers, all email correspondence with clients regarding business proposals, agreements, operations, quotations, and other related matters must include the following in copy. | Marketers
She advised booking should be done via email and key people should be copied.Additionally, all marketers are required to ensure you have reliable access to your emails while out in the field. This is essential for timely communication and smooth coordination with both clients and the internal team | Marketers
She reported found a speakers for the Men's mental Health program for the male staff on Monday. | Hazel
She advised to have the Christmas meeting on Tuesday ( 10th June 2025)
NOTES BY MANAGING DIRECTOR
She mentioned ahe will be briefly in attendance on Men's mental Health program for the male staff on Monday
She encouraged all the members to push to convert business more as month looking very promising in terms of revenue.
She suggested refine on December rates should be done the by adding Peak season. | Marketers
She mentioned we should add more content on fun day event for kids to have several activities | Marketers
She suggested team to come up with a polite Standard email body during cancellation of a booking to clients due to lack of space or during overbooked on same dates with other groups.
MINUTE 5: AOB:
MD mentioned board is working on adding more accomodation as the bussiness is booming and urge of more room is there.
The meeting ended at 1:05pm.
PROPOSER
NAME: ______________________________________ SIGN _______________________
DATE:
SECONDER
NAME: ______________________________________ SIGN _______________________
DATE:
SECRETARY
NAME: ______________________________________ SIGN _______________________
DATE:

## JUNE 19TH
MARKETING MEETING MINUTES
HELD ON JUNE 14th, 2025 (9:30AM - 12:14 PM) | ACTION PERSON | TIME
PRESENT
1. Hazel Wananyanga - Operations Manager (CHAIR)
2. Desmond Kithinji - Marketing Executive
3. Kelvin Murerwa - IT Manager
4. Valentine Wanjiku - Marketing Executive
5. Diana Arunga – Marketing Executive
6. William Juma- F&B Manager( Recording member)
7.George Ndegwa- F.O supervisor
IN ATTENDANCE
AGENDA
1. Matters arising from the reading of the previous minutes
2. Events
3. Marketers reports.
5. AOB.
The meeting commenced at 0932hrs with a word of prayer from Diana
MINUTE 1: MATTERS ARISING.(Reactions to previous minutes)
DJ Braniek to be invited after every 2 weeks and kelvin was tasked to follow up. | Kelvin
Kelvin is to prepare a contract outlining the entertainment guidelines from the members regarding the terms of engaging the DJ | Kelvin
Desmond shared that he visited the Nanyuki Children's Home and suggested that the group should organize a visit. He proposed that the Welfare Committee should schedule a suitable date for the visit. | welfare committee
Kelvin shared that he is experiencing a challenge integrating the M-Pesa data with Hotel Plus and is exploring alternative solutions. | Kelvin
Hazel advised that marketers should come up with budgets in prepation to visit magical expo by 28th. | Valentine,desmon ,diana
William shared that Father's Day recorded good sales, and the team also successfully shared Father's Day messages with the guests.
Desmond shared the Christmas flyer and noted that a few changes still need to be implemented. | Kelvin
MINUTE 2:1 EVENTS-FUNDAY
Members recommended contracting a panda mascot instead of a bunny, with accommodation costs excluded. | WILLIAM
William presented the familly funday checklist.He was advised to add key players and mostly the supervisors | WILLIAM
Members were tasked to focus on the fun day event and ensure tasks are completed | ALL
MINUTE 2:2 EVENTS(Christmas Day )
Hazel recommended holding another Christmas planning meeting on August 15th to discuss the way forward.
Members were tasked to prepare budgets,christmas programme,entertainment contracts for christmas planing
MINUTE 3:MARKETERS REPORT
Diana shared that the Laikipia Nature Conservancy group was pleased with their experience and expressed interest in returning
She reported that MCK St. Paul was satisfied with our services and plans to return. | Diana
She informed that the Food for the Hungry group will be returning next week and requested that pork be excluded from their menu. She also added that they will require body lotions in their rooms and tropical sweets during their meeting. | Diana
Desmond visited the following accounts
AGRICULTURAL FINANACE CO-OPERATIVE NANYUKI
NANYUKI LAW COURT
MARY IMMACULATE TEACHERS TRAINING COLLEGE
LIGHT FOR THE WORLD
JEMU EXPEDITIONS
SNV NANYUKI OFFICE
P.C.E.A MUTHAIGA
BRICKWOOD SCHOOLS
CENTRAD-NANYUKI
GREEN GENERATION INITIATIVE
He reported that Revenue achieved year to date: KES 227,950 which is 10.1% of His yearly target.
He advised that all marketers to update each other when visiting another persons account
Desmond was advised to skip valentines report for the nex meeting. | VALENTINE
NOTES BY DIANA:
She reported that Revenue achieved year to date: KES 2,430,390 which is 55.64% of her yearly target.
She shared that the 2Scale group recommended heating the swimming pool
She shared that she had visited Kikowasco and discovered they have payment issues. She was advised not to pursue the account further.
She shared that Rusinga School had been facilitated through a different hotel.
she shared that canvas are ready for sales this week
NOTES BY WILLIAM
He breifly took team on the funday budget pending approvals.
NOTES BY THE OPERATIONS MANAGER (CHAIR)
She advised marketers to finalize on bookinking cancelliation templete | Valentine, Desmond, Diana
She tasked kelvin with updating the CBE flyer | Kelvin
She instructed the marketers to review and revise the peak season rates for use during peak days. | Valentine, Desmond, Diana
She assigned Kones to speak with Reverend Wachai to arrange a motivational expert for men’s mental health. | kones
She emphasized the importance of unity and coordination among the marketers, instructing them to hold their own meetings, organize themselves, and report back to her. | Desmond
MINUTE 5: AOB:
Diana was tasked to share a propasal for the code bikes she recommended
The meeting ended at 12:14PM
PROPOSER
NAME: ______________________________________ SIGN _______________________
DATE:
SECONDER
NAME: ______________________________________ SIGN _______________________
DATE:
SECRETARY
NAME: ______________________________________ SIGN _______________________
DATE:

## JUNE 28TH
MARKETING MEETING MINUTES
HELD ON JUNE 28th, 2025 (9:30AM - 12:48 PM) | ACTION PERSON | TIME
PRESENT
1. Hazel Wananyanga - Operations Manager (CHAIR)
2. Desmond Kithinji - Marketing Executive
3. Kelvin Murerwa - IT Manager
4. Valentine Wanjiku - Marketing Executive
5. Diana Arunga – Marketing Executive (Recording member)
IN ATTENDANCE
1. Jane Gichuki- Managing Director
2. William Juma- F&B Manager
AGENDA
1. Invoicing training
2. Matters arising from the reading of the previous minutes
3. Marketers report
4. Events
5.Proposals
6.AOB.
The meeting commenced at 0932hrs with a word of prayer from William
MINUTE 1: INVOICING TRAINING
It was noted that all invoicing will be done directly to clients by the accounts office not reservations. | Grace
MINUTE 2: MATTERS ARISING FROM THE PREVIOUS MINUTES
It was proposed that we pertake in CSR on 5th September | Welfare
Welfare officials tasked to coordinate collection of donations | Welfare
MD advised we be strategic in alignment to events and artist performance since they don’t do too well in the mt Kenya region. | Marketers
She also proposed we reconsider having the band that performed last year over for this year’s Christmas.
It was states that all events are under marketers: Christmas -tasked to Valentine , Fun day- Desmond, Welfare CSR Coordination and blood drive-Diana | Marketers
Tasked to follow up on the nature conservancy payment | Diana
The paint activity was tasked to Hazel with the assistance of William | Hazel, William
It was reported that both Valentine and Diana are following up on getting the child artist contact. | Valentine,Diana
It was noted that we got a mental health speaker from Nanyuki to talk to the men in our company.
MD advised marketers to embrace working together so as to have synergy | Marketers
Tasked to follow up on the partnership with the children’s car ride personnel due to their inconsistency. | Hazel
MINUTE 3: MARKETERS REPORT
Desmond serviced the following accounts:
Rongai primary, P.C.E.A ST Paul, Victory academy, Naromoru township,SNV,Amref,Jacaranda health,Nanyuki law court,Aguthi primary
He reported that Revenue achieved year to date: KES 257,050 .
Valentine serviced the following accounts:
PACIDA, Action Aid, ASAL Network, Qabale Duba Foundation, SND, Marsabit Women Advocacy Development Organization, Collaborative Centre for Gender & Development, Oxfam in Kenya, Survivor and Community-Led Crisis Response, Marsabit Water and Sanitation (MARWASCO), Welt Hunger Hilfe, Population Council, Lewa Wildlife Conservancy, as well as the schools Snow View Academy, Good Shepherd, and Carmel Hill.
She reported that Revenue achieved year to date: KES 3,454,000
Notes by Diana:
She mentioned she was in for the week but was actively following up on capital sacco, sunshine academy, NDMA for oncoming business.
She reported that Revenue achieved year to date: KES 2,807,190
Notes by MD:
marketers were advised to do a list of organizations and the revenue being brought (conversion chart table | Marketers
Marketers were tasked to redo lawcourts since there is a reshuffle. | Marketers
Desmond was assigned KFS but it was recorded that the first business is direct business | Desmond
Marketers were tasked to know when to stop pushing for business, rather we should strategize so as not to overwhelm a client.
MD commended the good food we prepare here in Jaqanaz
We were advised that currency exchange rates can be done here at Jaqanaz and the exchange rate should be included as per our local bank rates.
Marketers were tasked to crack the Chinese market | Marketers
MINUTE 4: EVENTS
1.FUNDAY | Desmond (lead)
Preparations are in place; the updated flyer is out and boosted
Tasked to be in charge of the fun day | Desmond
The fun day budget was discussed
To report on the far we have gotten with microphone repair | Kelvin
The approved budget to work with for the artist of the day is 15,000
We were tasked to get options for mascots for the funday, to make it more vibrant and to minimize monotony. | William
Valentine mentioned that she reached out to good Shephard Nyeri and shared the fun day flyer
Marketers were tasked to follow up on conversions for the fun day | Marketers
2.CHRISTMAS | Valentine (lead)
It was stated that the proposed Christmas rates were competitive and were approved effective 10th December 2025- 5th January 2026
It was stated that only those on business ventures i.e. conferences will not be affected by the rates
We went through the Christmas rate card and programe.
Tasked to select attires staff can easily access for the themes and that we should consider flexibility in movement while wearing the selected attires.
Mascot was proposed to come in on 1st not 31st
Tasked to include casuals and trainees in the planning to for ease in allocation
Logistics to be discussed in the next meeting | Committee | 15/7/2025
MINUTE 5: PROPOSALS
1. STUDENT PACKAGES
It was presented by valentine
It was stated that basic meal should come with a description on what it entails to give a distinguishing point and a costing should be done on the packages | Grace& Marketers
Time bound activities should be included in the package description i.e. team builder sessions
Tasked to get better wordings for description of activities.
Timeline on completion |  | 2025-04-07
2. EXPOS 2025
Marketers tasked to attend the Sarit and magical Kenya expo as visitors a day in each Expo. Preferably the second day. | marketers
We were advised not to go in with our branded uniform and merchandise
3. POWER POINT PITCH
It was presented by Desmond
We were advised to stop repeating photos, work on justification, and photo positioning
The I love Naromoru signage to be used on the last page.
4.CHRISTMAS
Marketers to come in on Tuesday to finalize on all pending tasks proposals and events | marketers
Improve on the Christmas flyer background picture | Kelvin
Have an outlined depiction of the budget allocation and variances from the other years. | Grace | 2025-01-07
We were advised to work with last years entertainment budget
We were advised to partner with solio in alignment to get a collaboration on discounted park fee entrance | Hazel
MINUTE 5: AOB:
The Tuesday meeting was approved
Marketers were tasked to give rooming lists of their clients coming in for the week
Tasked to call Africa one informing them on the possibility of a spillover of our guests | Hazel
Valentine mentioned we will be more united
MD announced a new role open from the board Business development officer and advised us to apply
MD mentioned creativity and innovations nominated by the board should be awarded in the MSM
She commended the good job done by the marketers and urged us to keep converting. | Hazel
Meeting ended at 12:48pm with a word of prayer by Desmond
PROPOSER
NAME: ______________________________________ SIGN _______________________
DATE:
SECONDER
NAME: ______________________________________ SIGN _______________________
DATE:
SECRETARY
NAME: ______________________________________ SIGN _______________________
DATE:

## JULY 8TH
MARKETING MEETING MINUTES
HELD ON JULY 8th, 2025 (9:30AM - 11:54 AM) | ACTION PERSON | TIME
PRESENT
1. Hazel Wananyanga - Operations Manager (CHAIR)
2. Desmond Kithinji - Marketing Executive
3. Kelvin Murerwa - IT Manager
4. Valentine Wanjiku - Marketing Executive (Recording member)
5. Diana Arunga – Marketing Executive
IN ATTENDANCE
1. Jane Gichuki- Managing Director
AGENDA
1. Matters arising from the reading of the previous minutes
2. Marketers report/Turn over /New accounts
3. Events
4.Proposals
5.AOB.
The meeting commenced at 0932hrs with a word of prayer from Valentine
MINUTE 1: MATTERS ARISING FROM THE PREVIOUS MINUTES
MD reported that the dollar account was in process and would be opened after the meeting. | MD
Diana reported that she announced about the blood drive to all the staff and is yet to get a definite number of those interested in donating.
MD advised that it should be well trained durin the MSM so the staff understand the benefits. | Diana
Staff were informed about the CSR event.MD advised that the collection of the items is done atleast 2 weeks before the date and that all the stuff donated should be vetted.
Hazel advised to still follow up on the Chinese market and how it can be penetrated. | Hazel
MINUTE 2: MARKETERS REPORT
Desmond serviced the following accounts:
P.C.E.A ST PAUL ACADEMY - NARUMORU
NAROMURU TOWNSHIP PRI SCH
IRIGITHATI PRIMARY SCHOOL NAROMORU
RONGAI PRIMARY SCHOOL NAROMORU
AGUTHI PRIMARY SCHOOL NAROMORU
P.C.E.A ST MUNYU CHURCH
NANYUKI LAW COURT
THINGITHU BOYS SECONDARY SCHOOL- NANYUKI
P.C.E.A MUTHAIGA - NANYUKI
Wildlife Research And Training Institute (WRTI)
He reported revenue achieved 257,050 out of 4,020,000
Valentine serviced the following accounts:
Kenya Institute For Public Policy Research Analysis
The mawazo Institute
Kenya National Innovation agency
Growth Africa
International rescue committee
Kenya Water for Health Organization
Evidence Action
Engineers Without Borders
CARE
REFERRALS FROM KENYA WATER FOR HEALTH ORGANIZATION
Water Sector Trust Fund
National Water Storage Authority
Water Aid
RTI International
Water Resources Institute
The water Project
Global Water centre
Save the children
She reported that she was going to allocate the marketers above referrals to follow up on.
She reported that Revenue achieved year to date: KES KES 3,548,715 out of 8,304,000
She reported pending payment from Taifa Sacco-174,000 and Murang'a county-420,000
Diana Serviced the following accounts
ST.Lwanga
Shalom Academy
Laikipia Permaculture
Gatei primary
Ihithe primary
Gathinga primary
Mirichu primary
Kangaita primary
kigogoini primary
She reported that Revenue achieved year to date: KES KES 1,733,890 out of 6,030,000
She reported pending payment of 1,425,900 from Rain Forest alliance and Food for Hungry.
MINUTE 3: EVENTS
1.FUNDAY | Desmond (lead)
Diana reported that the kid artist price was not equivalent to the value that the event anticipates.
It was proposed and approved to get 2 mascots instead of getting the artist.
Marketers made a report of the schools they are following up on for the event.
Desmond
St Pauls Munyu-50 pax
Aguthi Primary-70 pax
Valentine
Good Shephered Nyeri-50 kids
Snow View Academy-50 kids
Still following up on Trainsview academy and Carmell Hill.
Diana
She reported she did not have any prospect but was following up on Shalom Academy that were planning for their fun day on 18th July.
Reported that she is following up On St. Lwanga and was advised to visit the church offices.
MD advised that we focus on schools with proximity to the hotel.
MINUTE 4: PROPOSALS
1. STUDENT PACKAGES
It was presented by valentine
She presented the packages costing that was within the costing and was approved.
Time bound activities should be included in the package description i.e. team builder sessions
She shared that both the silver and bronze lunch & dinner package meals would include -: (1 salad,2 Starch,1 meat Item,1 dessert,1soft drink,1 Fruit slice)
The gold package meals will include-:(1 salad,3 starch,2 meat items,1 vegetable,1 soft drink,1 dessert,1 fruit slice)
MD was concerned that the two did not have any differentiating factor but the prices were varying.It was advised that we maintain the packages because of the activities.
It was advised that Diana should sell the approved packages to Joseph.
2. EXPOS 2025
Diana should still follow up on the entrance fees for Magical Kenya Expo. | Diana
Valentine did the presentation of the budget for the Hotel Expo happening at KICC on 6th -8th August.MD advised that she keeps updating and keep tabs to avoid missing out on attendance.
She was advised to share the budget via email. | Valentine
Notes by OM
She advised that any marketer that was caught poaching business from the front office,the penalty of 6 factor would be implemented to their revenues achieved.
She also advised that the receptionist that would be found to have "Sold" business to the marketer,would qualify for automatic dismissal.
Marketers were advised to report all the accounts via email prior to check in of the guests.
Notes by MD:
MD got a call from Mr. Michael from Sunshine academy about their booking.A discussion was had about servicing the group that will check in on 27th-29th July -110 pax.
The approved rate for the group is 4500 per student but should be renegotiated for their next bookings.
MD reported that she is purchasing extra beds and advised Hazel to follow up on getting extra linen to accommodate the group.
MD enquired about the Food for Hungry Marsabit that are supposed to check in next week.Hazel reported that she was incharge of the group but it was advised that Diana should service the group. | Diana
MD advised that marketers should focus more on conversions and not fighting over accounts.She advised that any groups that marketers and Front office would not agree on would be allocated to her.She would be the last word in accounts mitigations.
She also advised that until the Front office had strong and dedicated leadership,all the sensitive groups that would be booked direct will be assigned to the marketers and in intervals.
She advised the marketers to sit down and discuss the departments SOPs and come up with a document that would be presented to her and the OM to give their input. | Marketers
MINUTE 5: AOB:
Valentine presented a Marketing department monthly training schedule as follows-;
TOPIC
Team Work & Collaboration -8th July 2025 | DIANA ARUNGA
Sales Technique -12th July 2025 | VALENTINE W.
Time Management & Prioritization-19th July 2025 | DESMOND
Digital Marketing & social media-2nd August 2025 | KELVIN
Booking & Reservations-29th July 2025 | GEORGE/Hazel
Conflict Resolution-9th August 2025 | MD
She also reported that the Tour Operators were appreciating the Hotel and she had a few tenative bookings for swimming,Steam and Sauna.
Kelvin was urged to convert business.He reported that he was following up on a client for the gym.
Meeting ended at 11:54am with a word of prayer by Kelvin.
PROPOSER
NAME: ______________________________________ SIGN _______________________
DATE:
SECONDER
NAME: ______________________________________ SIGN _______________________
DATE:
SECRETARY
NAME: ______________________________________ SIGN _______________________
DATE:

## JULY 12TH
MARKETING MEETING MINUTES
HELD ON JULY 12th, 2025 (9:30AM - 10:54 AM) | ACTION PERSON | TIME
PRESENT
1. Hazel Wananyanga - Operations Manager (CHAIR)
2. Desmond Kithinji - Marketing Executive(Recording member)
3. Kelvin Murerwa - IT Manager
4. Valentine Wanjiku - Marketing Executive
5. Diana Arunga – Marketing Executive
6.George Ndegwa- Front office supervisior
IN ATTENDANCE
1. William Juma- FN&B Manager
2. Grace Huho- Head Accounts
AGENDA
1. Matters arising from the reading of the previous minutes
2. Marketers report/Turn over /New accounts
3. Events
5.AOB.
The meeting commenced at 09:34hrs with a word of prayer from Diana
MINUTE 1: MATTERS ARISING FROM THE PREVIOUS MINUTES
Valentine to announce CSR initiative to welfare members during MSM on 14th July. | Valentine
Hazel mentioned she is still following with Chinesse markets. | Hazel
Diana mentioned all booking under Joseph to be removed on projections. | Diana
Hazel mentioned Tujienjoy Group is same booking under Mr. David
MINUTE 2: MARKETERS REPORT
Desmond serviced the following accounts:
Munyu Primary School/Church
Furaha Primary School
Kihato Primary
2nk Sacco Society
Kenya Red Cross Central Region Office
Rainbow Agrosciences
Kmtc -Othaya
Wanainchi Dt Sacco
He reported revenue achieved 350,050 out of 4,020,000
Valentine serviced the following accounts:
Kenya Institute For Public Policy Research Analysis
The mawazo Institute
Kenya National Innovation agency
Growth Africa
Evidence Action
Juja Preparatory
Stepping Stones Preparatory
She reported that she had no prospect groups for next week.
She reported that Revenue achieved year to date: KES KES 3,548,715 out of 8,304,000
Diana Serviced the following accounts
MERUWASCO
MEWASS
Meru County Assembly
A.I.P.C.E.A
Ripples international
CIFORD Kenya
CARITAS
MECAWE
She reported that Revenue achieved year to date: KES KES 2,465,190 out of 6,030,000
She reported pending payment of 904,680
MINUTE 3: EVENTS
1.FUNDAY | Desmond (lead)
Hazel mentioned checklist and budget to be shared | Desmond
Juma following up from Mascot kenya for updated contarct on 2 mascots. | Juma
Panda and Pony Mascots were selected for the fun day.
Notes by OM
Hazel mentioned Sunshine Academy to make a deposit. | Diana
She mentioned deposit is to facilitite on cost for buying linens and other logisistics for group.
She mentioned all communactaion from Food for the hungry Marsabit will go through her.
Advised Valentine to set Muranga all departments with use same flat rates. | Valentine
Adviced Desmond to make a checklist/Program and updated budget and share | Desmond
Notes by Juma:
Juma mentioned working with chef to come up with Fun day snacks set menu.
Notes by Grace:
She mentioned to Diana to advice Sunshine to bring personal effects. | Diana
She mentioned to Diana to get sunshine school program on trip.
She adviced Diana to share with school menu.
Notes by George:
He give update on Magutu travellers that he is still following on leads
Mentioned Food for Hungry have updated their booking dates to 16th July 2025 -20th July 2025
Mentioned he is following on George Mbuto for mbuzi package abouth 300-400 pax.
MINUTE 5: AOB:
Valentine presented a Marketing department monthly training schedule as follows-;
TOPIC
Team Work & Collaboration -8th July 2025 | DIANA ARUNGA
Sales Technique -12th July 2025 | VALENTINE W.
Time Management & Prioritization-19th July 2025 | DESMOND
Digital Marketing & social media-2nd August 2025 | KELVIN
Booking & Reservations-29th July 2025 | GEORGE/Hazel
Conflict Resolution-9th August 2025 | MD
Hazel emphasised team to keep up and converstion.
Meeting ended at 10:54am with a word of prayer by Valentine.
PROPOSER
NAME: ______________________________________ SIGN _______________________
DATE:
SECONDER
NAME: ______________________________________ SIGN _______________________
DATE:
SECRETARY
NAME: ______________________________________ SIGN _______________________
DATE:

## JULY 19TH
MARKETING MEETING MINUTES
HELD ON AUGUST 02ND , 2025 (9:32AM - 12:01 PM) | ACTION PERSON | TIME
PRESENT
1. Hazel Wananyanga - Operations Manager
2. Desmond Kithinji - Marketing Executive
3. Kelvin Murerwa - IT Manager
4. Valentine Wanjiku - Marketing Executive
5. Diana Arunga – Marketing Executive
6.George Ndegwa- Front Office Supervisior
IN ATTENDANCE
1. Jane Gichuki - Managing Director
1. William Juma- FN&B Manager
AGENDA
1. Matters arising from the reading of the previous minutes.
2. Post analysis
3. Marketers report/Turn over /New accounts and weekly projection.
4. Aob
The meeting commenced at 0932 hrs with a word of prayer from George
MINUTE 1: MATTERS ARISING FROM THE PREVIOUS MINUTES
Desmond reported that together with Valentine he will be going to Nairobi in coming week, to service the new accounts introduced to him by Valentine. He also confirmed that he called FIPS Africa and shared his number for prompts anytime since they didn’t have any upcoming activities. Again he reported that he had talked with Joe and requested him to share his catalogue or come personally to the hotel for further discussion. He didnt have a conclusive feedback from him | Valentine/Desmond
Valentine reported that she is following up with speckled bird and has shared our chrismas rates with them for review. Concerning Tembea Kenya she confirmed sharing email awaiting feedback from them. | Diana
MD reccommended that we engage Joe since we have the facilities he needs and we benefit with his marketing for clients.
MINUTE 2: MARKETERS REPORT
Desmond serviced the following accounts:
Amiran Kenya
2nk Sacco
Pcea Nyeri Presbytery Offices
Ckl Africa ltd
Caritas
MFB Bank Nyeri
Tower Sacco Nyeri
New Fortis Sacco Nyeri
Nanyuki law Courts
SNV Nanyuki Office
He reported revenue achieved was 477,050 out of 4,020,000.
New accounts- Mukangu Pcea & Itiati Pcea. To visit International religion as his account partnering with Valentine to guide him on how to pitch for the account.
Valentine serviced the following accounts:
Communication Authority Nyeri
Epra Nyeri
Micro Cap Holding Nyeri
Othaya water and sanitation
CFAO Nyeri
Northern Range Land Trust Nanyuki
Action kenya Initiative
Moof Africa
Sangida Foundation Nanyuki
Unilever Nanyuki
Follow up accounts
Corteva Nairobi
Micro Holding Nairobi
Phillips Kenya
Global Compact Kenya
Loyal Adventures
She reported that Revenue achieved year to date: KES KES 3,757,375 out of 8,304,000
Pending Payments
Muranga County- 420,000
Child Fund- 40,700
Icea Lion- 12,000
Diana Serviced the following accounts
Rainforest Alliance
Kerugoya law courts
Kerugoya Fortis Medical and cancer center
Pcea Presbytery Offices
Immaculate Catholic Church
Tess Kimotho and Advocates
Agricultural sector Development and Support Programme
New Accounts
Laikipia Conservancy
Sunshine School
Political Group
She reported that Revenue achieved to date: KES KES 4,727,870 out of 6,030,000
MINUTE 2.1: PROJECTION
George presented the month's projection. | Desmond & Valentine
MINUTE 3: EVENTS
1.FUNDAY | Desmond (lead)
Desmond presented the kids' funday checklist and it was agreed that it should also be discussed on Monday 21st. There were only a few purchases left.
Marketers reported that exams were starting on Monday 21st thus many schools said they will not be able to bring in kids as institutions. To boost walk-in numbers, marketers asked Kelvin to print mini funday flyers so that teachers can give students to take home.
Diana reported that she had spoken to Director Kihagi of Shalom schools for future partnership. She mentioned that he is open to bringing kids in every term.
Diana mentioned that public schools like Naromoru Township were concerned about the "no snacks" approach for the kids funday. It was agreed that the teacher can organize for the snacks for easy control.
Desmond was tasked with following up on Joe on service provision for future fundays.
Kelvin was asked to follow up on purchase of new microphones. | Kelvin
Notes by OM
Hazel directed that there should always be a GRO(A marketer) by the swimming pool on weekends. | All
She tasked Valentine to look for an on call masseuse after Desmond reported that we have had several guests ask for one. | Valentine
She also requested Juma to share hall allocation for all the groups.
She directed that all interns would be in housekeeping department on Sunday and Monday.
Notes by MD:
She tasked valentine to find out what it takes for the resort to be featured on Tembea Kenya magazine after the bootcamp is up and running. | Valentine
On contested accounts, she guided that if an account has been inactive for a long time and someone else successfully activates it then the group goes to the activator. She also guided that all contested accounts should be presented to Hazel for guidance. | Marketers
MINUTE 5: AOB:
Agenda 4 on SOPs was postponed to a later date.
Kelvin was asked to hasten editing of gym content.
Marketers were asked by the OM to report back on Thursday 24th for preparations.
Kelvin briefed the team about the new board initiative to revamp the company's online presence which would need all marketers on deck for good results. He said he would share more once he and Jack are ready.
Diana sought clarification on guest extras charged to a marketer's account. Hazel advised that extras are not commissionable but they add to the marketer's total turnover.
Meeting ended at 12:54pm with a word of prayer by Valentine.
PROPOSER
NAME: ______________________________________ SIGN _______________________
DATE:
SECONDER
NAME: ______________________________________ SIGN _______________________
DATE:
SECRETARY
NAME: ______________________________________ SIGN _______________________
DATE:

## AUGUST 2ND
MARKETING MEETING MINUTES
HELD ON AUGUST 02ND , 2025 (9:32AM - 12:01 PM) | ACTION PERSON | TIME
PRESENT
1. Hazel Wananyanga - Operations Manager
2. Desmond Kithinji - Marketing Executive
3. Kelvin Murerwa - IT Manager
4. Valentine Wanjiku - Marketing Executive
5. Diana Arunga – Marketing Executive
6.George Ndegwa- Front Office Supervisior
IN ATTENDANCE
1. Jane Gichuki - Managing Director
1. William Juma- FN&B Manager
AGENDA
1. Matters arising from the reading of the previous minutes.
2. Marketers report/Turn over /New accounts and weekly projection.
3. Post analysis
4. Aob
The meeting commenced at 0932 hrs with a word of prayer from George
MINUTE 1: MATTERS ARISING FROM THE PREVIOUS MINUTES
Desmond reported that together with Valentine he will be going to Nairobi in coming week, to service the new accounts introduced to him by Valentine. He also confirmed that he called FIPS Africa and shared his number for prompts anytime since they didn’t have any upcoming activities. Again he reported that he had talked with Joe and requested him to share his catalogue or come personally to the hotel for further discussion. He didnt have a conclusive feedback from him. | Valentine/Desmond
Valentine reported that she is following up with speckled bird and has shared our chrismas rates with them for review. Concerning Tembea Kenya magazine she confirmed sharing email awaiting feedback from them. | Valentine.
MD reccommended that we engage Joe since we have the facilities he needs and we benefit with his marketing for clients.
MINUTE 2: MARKETERS REPORT
Desmond serviced the following accounts:
Amiran Kenya
2nk Sacco
Pcea Nyeri Presbytery Offices
Ckl Africa ltd
Caritas
MFB Bank Nyeri
Tower Sacco Nyeri
New Fortis Sacco Nyeri
Nanyuki law Courts
SNV Nanyuki Office
He reported revenue achieved was 477,050 out of 4,020,000.
New accounts- Mukangu Pcea & Itiati Pcea. To visit International religion as his account partnering with Valentine to guide him on how to pitch for the account.
Valentine serviced the following accounts:
Communication Authority Nyeri
Epra Nyeri
Micro Cap Holding Nyeri
Othaya water and sanitation
CFAO Nyeri
Northern Range Land Trust Nanyuki
Action kenya Initiative
Moof Africa
Sangida Foundation Nanyuki
Unilever Nanyuki
Follow up accounts
Corteva Nairobi
Micro Holding Nairobi
Phillips Kenya
Global Compact Kenya
Loyal Adventures
She reported that Revenue achieved year to date: KES KES 3,757,375 out of 8,304,000
Pending Payments
Muranga County- 420,000
Child Fund- 40,700
Icea Lion- 12,000
Diana Serviced the following accounts
Rainforest Alliance
Kerugoya law courts
Kerugoya Fortis Medical and cancer center
Pcea Presbytery Offices
Immaculate Catholic Church
Tess Kimotho and Advocates
Agricultural sector Development and Support Programme
New Accounts
Laikipia Conservancy
Sunshine School
Political Group
She reported that Revenue achieved to date: KES KES 4,727,870 out of 6,030,000
MINUTE 2.1: PROJECTION
George presented the month's projection and noted that Habitat for Humanity has confirmed most bookings running through the whole month in different specifications. Other bookings include buffet breakfast for 13 pax on Saturday 9th booked by Morris and booking.com accommodation on 29th/30th August.
MINUTE 3: POST ANALYSIS
1.FUNDAY
Fun day post analysis was presented by Valentine where by she reported that perfomance for the day was below our expectations and we didn’t get any returns as profits, we managed to pay for the services only. Further she noted that we failed to capture most schools kids since we failed to allign with the schools calender. Desmond echoed the same and recommended we be involving the schools when planning for kids fun day to avoid failures and be able to align with their calenders. | Marketers
Marketers reported that they will be visiting schools 1st week after opening to do vigourous marketing for the next kids fun day. MD advised them to align with one teacher who will be assisting them on coordination. To break even they should start early and find a consultant teacher to be consulting with. She advised that the marketing team owes us a kids fun day since last one didnt perform well and that it should perfom. | Marketers
Another issue raised by Wiliam was about Mascots. We expected them early in the morning but they came late in the afternoon and caused delays in their perfomance. It was suggested that it would have been better to accommodate them day before the performance to mitigate the issue of delays, with it effected charges should reflect on their account. For future purposes we should maybe introduce lateness fee. | All
Kelvin reported that DJ and MC were well coordinated and that we should lock them in as a pair for our events. He had the sound repaired prior to the event date hence the perfect sound experienced during the event day. | Kelvin
Diana was picked to lead the next kids fun day. | Diana
There was a suggestion made that we plan for a family fun day and the OM gave a nod on it and cosidered doing it as a family Sunday during this August Holiday and remember to take our lesson from the last family fun day, also check on how to accommodate teenagers through activities that will suit them. The Md requested us to think through and fast for the same. | All
2. SUNSHINE SCHOOL.
Diana report: Everything was on check, the preparation were done on time. The only concern we had was lack of proper coordination from the schools side for example they didn’t have a full record of their students which resulted to room reallocation. There was also an issue with one of their student who was allocated a room alone.
Issues raised by sunshine.
1.Cold showers - noteably in series 2, 3 and 5. series 1 was caused by power tripping in 106 & 107. Mitigation is to provide instant showers for alternative showers.
2. They felt that the restaurant closed earlier that their expectation which was 24 hours.
3. We didn’t have variety of activiries. Teen activities to be improved
4. Smart TV aspect was an issue also.
5. Positive: Our team was orderly and very warm, meals were okey.
From IT desk: booking.com platform is up and active and has handed over to George for follow ups, still working for Expedia. | George/ Kelvin
To present a conclusive report from Jack and also on content creation. | Kelvin
From William: Juma recommended on Pizza offers to maximise sales since he has realised our pizza sales are going down | William
From the OM Desk
Urged the team to take advantage of expo on 7th to service accounts and marketing | Marketers
Pointed valentine to be inchange of our events calender. | Valentine
Requested Diana to coordinate the next kids fun day. | Diana
Noted that Sauna and steam bath sales are very low and requested us to look unto how we can improve o the sales. | All
MD DESK
Madam was pleased with the effort and team work put during the weekend and thanked everyone, she urged all us to put more effort on selling August. | All
MINUTE 5: AOB:
Kelvin - The staff gave a positive reaction after the Saturday events especially in cleaning.
Om - Kelvin to make a list of maitenance issues reported for followup when Kones reports back.
MD - Think about charges on the upcoming heated heated swimming, as we also do bench marking around for the same.
Meeting ended at 12:01pm with a word of prayer by Valentine.
PROPOSER
NAME: ______________________________________ SIGN _______________________
DATE:
SECONDER
NAME: ______________________________________ SIGN _______________________
DATE:
SECRETARY
NAME: ______________________________________ SIGN _______________________
DATE: